Healthy URBan Environment: Developing Higher Education in Architecture and Construction in Bosnia and Herzegovina / HURBE

Quality Report

Work Package 3

Dates: 15 November 2018 – 14 November 2021

Quality report WP 3

15 November 2018 – 14 November 2021

Lead Organisation P3: Faculty of Architecture University of Zagreb

| Type of report | final WP quality report | 15/11/ 2018_ 14/11/ 2021 |
| --- | --- | --- |
| Work package type and ref.nr | DEVELOPMENT | 3 |
| WP 3 Title | Permanent laboratories |  |
| Lead Organisation | P3. Faculty of Architecture University of Zagreb AF ZG |  |
| Date | 14.11.2021. |  |
| Quality report number | 02 |  |
| WP Start Date | 15-04-2020 |  |
| WP End Date | 14-11-2021 |  |

| Related assumptions and risks | In relation to the related project assumptions (Detailed project description page 65 of 127): - There is a strong interest from the Bosnian HEIs in setting up permanent laboratories and their network Were there any risks for the delivery of the workpackage? Yes, there has been the following risk: - There are some administrative obstacles in some Partner Universities that stand in the way of respecting the project’s Gantt. If there were risks, how did you encounter them? - WP3 lead organisation give them support with some administrative solutions. |
| --- | --- |
| Description of WP | This work package upgrades facilities by installing permanent laboratories of HURBE that support the implementation of innovative practices for the teaching methods and the development of new services - for HEI and other institutions - in the Partner Country. UNSA, UNZE and UNMO identified the necessary spaces inside their universities for Laboratories. They presented space for laboratories in the Lab Visit in Rome. Lab visit was held from 17.02.2020. to 19.02.2020. UNSA, UNZE and UNMO were finished with the purchase of equipment. The purchased equipment was installed in the identified laboratory spaces in UNSA, UNMO and UNZE. |
| Tasks development | Task 3.1: Preparation of permanent laboratories. Finished. Task 3.2: Installation of permanent laboratories. Finished. Task 3.3: Foster the HURBE Network with other laboratories. In progress. Task 3.4: Internship for students. Finished. |
| WP Start Date | 15-04-2020 |
| Description tasks | Task 3.1: Preparation of permanent laboratories: Members from Partner Country HEIs flew to Rome and visited the existing laboratories at the University of UNIROMA. The following professors visited UNIROMA1: 2 professors, one technical staff member and one PhD student from UNSA, 2 professors, one technical staff member and one PhD student from UNZE, and 2 professors and one technical staff member and one PhD student from UNMO. UNSA, UNZE and UNMO identified the necessary spaces inside their universities for Laboratories. They presented identified laboratory space for laboratories in Lab Visit in Rome. Lab visit was held from 17.02.2020. to 19.02.2020. at the Sapienza University of Rome, Rome. UNSA, UNZE and UNMO finished tender procedures in order to purchase the required equipment. UNZE, UNMO and UNSA finished with the purchase of equipment. The purchased equipment was installed in the identified laboratory spaces at the UNSA, UNMO and UNZE. Task 3.2: Installation of permanent laboratories: UNZE, UNMO and UNSA followed the purchase and arrival of the chosen equipment. Then, the purchased equipment was installed in the identified laboratory spaces in each university with the participation of the staff of the laboratories. The Programme Country HEIs coordinated with Partner Country HEIs to guarantee the correct installation and functioning of the installed equipment. Task 3.3. Foster the HURBE Network with other laboratories. The installed laboratories signed cooperation agreements with similar laboratories in UNIROMA1, AF ZG and UACEG in the field of Healthy Urban Environment. Task 3.4. Internship for students The Consortium identified the selection criteria for the internship of the Bosnian students inside the laboratories. Each of UNSA, UNZE and UNMO selected students for the internship. Partner Country Universities made Internship plan and Internship regulations for each University. They also have an attendance sheet for using lab equipment. At the end of the Internship, students submitted a report called Internship diary of their activities and received a certificate from their University. |
| Outputs and Outcomes | T3.1: Event, training material, product. T3.2: Product T3.3: Product T3.4: Product |
| Indicators of progress | T3.1: Lab Visit was held, purchase was finished T3.2: UNZE, UNSA and UNMO installed equipment T3.3: Agreements were signed with HURBE members T3.4: 11 Students on Internship at UNMO, 10 students on Internship at UNZE and 15 students on Internship at UNSA. |
| How were indicators of progress measured? | T3.1: Lab visit attendance sheets, pictures and presentations, documents for public procurement of equipment, documents allocating space to the laboratories T3.2: Invoice for the purchased equipment, pictures of equipment T3.3: Signed Agreements T3.4: Attendance sheets, Student’s diary, pictures |
| Comments | WP tasks are successfully finished. Task 3.3 is in progress. |
| Corrective measures | Project coordinator and WP3 lead organisation have been monitoring the tasks development to fill the work package and tasks requirements on time. There were some delays in public procurement of equipment. |